## The Problem
Park and Ride Project
A large Southeast city is requesting federal funding for a park-and-ride project.
One of the requirements in the request application is a network plan for the design phase of the project,
Sophie Kim, the chief engineer, wants you to develop a project network plan to meet this requirement.
She has gathered the activity time estimates and their dependencies shown here.
Show your project network with the activity early, late, and slack times. Mark the critical path.
ID | Description | Predecessor | Time
A | Survey | None | 5
B | Soils Report | A | 20
C | Traffic Design | A | 30
D | Lot Layout | A | 5
E | Approve Design | B, C, D | 80
F | Illumination | E | 15
G | Drainage | E | 30
H | Landscape | E | 25
I | Signage | E | 15
J | Bid Proposal | F, G, H, I | 10

## Park-Ride Worksheet
Park and Ride
|  |  | 5 | B | 25 |  |  |  | 115 | F | 130
|  |  | 10 | Soils Report |  |  |  |  | 15 | Illumination
|  |  | 15 | 20 | 35 |  |  |  | 130 | 15 | 145
0 | A | 5 | 5 | C | 35 |  |  |  | 115 | G | 145
0 | Survey |  | 0 | Traffic Design |  |  |  |  | 0 | Drainage
0 | 5 | 5 | 5 | 30 | 35 | 35 | E | 115 | 115 | 30 | 145 | 145 | J | 155
[6 empty] | 0 | Approve Design |  |  |  |  | 0 | Bid Proposal
[6 empty] | 35 | 80 | 115 |  |  |  | 145 | 10 | 155
|  |  | 5 | D | 10 |  |  |  | 115 | H | 140
|  |  | 25 | Lot Layout |  |  |  |  | 5 | Landscape
|  |  | 30 | 5 | 35 |  |  |  | 120 | 25 | 145
Legend
ES | ID | EF | [6 empty] | 115 | I | 135
SL | Descrip | [7 empty] | 10 | Signage
LS | Dur | LF | [6 empty] | 125 | 20 | 145
Legend
ES | ID | EF
SL | Descrip
LS | Dur | LF